## Sheet1
Team Number: 3
TEAM SCHEDULE
On this schedule, you will plan the successful completion of all Task deliverables, using the resources of the whole team.
Each team must maintain one version of this schedule. The manager of the team is responsible for keeping this schedule up to
date and for making sure that everyone on the team has access to the latest version of it.
Every job in the schedule (i.e. line in the spreadsheet) must have exactly one name in the column for Person Responsible.
Below I have listed jobs required to complete the four Tasks. You must completely fill in the whole schedule with
names, dates and times before submitting Task 1.You will need to add rows with additional jobs that your team must complete.
For example, you will need one line in the schedule for each team member that will be reviewing each document. The only columns
to be left blank for now are the "Date and Time Completed" and "Person Completing".
You will fill those columns in as each job is completed. Do not start the project until every team member understands
what every one of these jobs entail! Ask any questions during a meeting or in the public Discussion.
|  | Date and | Person |  | Date and Time | Person
ID # | Job Name | time due | Responsible | Predecessors | Completed | Completing
Jobs required for Task 1
1.0 | Draft of schedule to team | 11/16/2016 1PM | Kevin |  | 11/16/2016 1PM | Kevin
1.1 | Feedback on schedule | 11/17/2016 8PM | Kris | 1.0 | 11/17/2016 8PM | Kris
1.2 | Final Schedule to Elaine | 11/21/2016 1PM | Kevin | 1.1 | 11/21/2016 10AM | Kevin
1.3 | Draft of contract to team | 11/16/2016 1PM | Kevin |  | 11/16/2016 1PM | Kevin
1.4 | Feedback on contract | 11/17/2016 8PM | Ricardo | 1.3 | 11/17/2016 8PM | Ricardo
1.5 | Final contract to Elaine | 11/21/2016 1PM | Kevin | 1.4 | 11/21/2016 10AM | Kevin
Jobs required for Task 2
2.0 | First draft of class skeleton to team | 11/18/2016 1PM | Kris | 1.2, 1.5 | 11/21/2016 10PM | Kris
2.1 | First draft of list of prewritten classes to team | 11/18/2016 1PM | Ricardo | 1.2, 1.5 | 11/21/2016 10PM | Ricardo
2.2 | First draft of UI design to team | 11/18/2016 1PM | Kevin | 1.2, 1.5 | 11/21/2016 10PM | Kevin
2.3 | Feedback on class skeleton to author | 11/21/2016 5PM | Kevin | 2.0 | 11/22/2016 10PM | Kevin
2.4 | Feedback on list of prewritten classes to author | 11/21/2016 5PM | Kris | 2.1 | 11/22/2016 10PM | Kris
2.5 | Feedback on UI design to author | 11/21/2016 5PM | Ricardo | 2.2 | 11/22/2016 10PM | Ricardo
2.6 | Second Draft of all documents to Elaine | 11/23/2016 1PM | Kevin | 2.3, 2.4, 2.5 | 11/23/2016 9:07AM | Kevin
2.7 | Feedback on all three documents from Elaine | 11/24/2016 1PM | Elaine | 2.6 | 11/23/2016 1:33PM | Elaine
2.8 | Third draft of class skeleton to team | 11/28/2016 5PM | Ricardo | 2.7 | 11/25/2016 10PM | Ricardo
2.9 | Third draft of list of prewritten classes to team | 11/28/2016 5PM | Kevin | 2.7 | 11/25/2016 10PM | Kevin
2.10 | Third draft of UI design to team | 11/28/2016 5PM | Kris | 2.7 | 11/25/2016 10PM | Kris
2.11 | Feedback on class skeleton to author | 11/29/2016 1PM | Kris | 2.8 | 11/28/2016 10PM | Kris
2.12 | Feedback on list of prewritten classes to author | 11/29/2016 1PM | Ricardo | 29 | 11/28/2016 10PM | Ricardo
2.13 | Feedback on UI design to author | 11/29/2016 1PM | Kevin | 2.10 | 11/28/2016 10PM | Kevin
2.14 | Fourth draft of all documents to Elaine | 11/30/2016 1PM | Kevin | 2.11, 2.12, 2.13 | 11/30/2016 11AM | Kevin
2.15 | Feedback on all documents from Elaine | 12/1/2016 1PM | Elaine | 2.14 | 11/30/2016 3:30PM | Elaine
Jobs required for Task 3
3.0 | Implementation of Person Class | 12/2/2016 1PM | Kevin | 2.15 | 12/1/2016 10PM | Kevin
3.1 | Feedback on Person Class | 12/3/2016 1PM | Kris | 3.0 | 12/2/2016 11AM | Kris
3.2 | Implementation of TestPerson Class | 12/2/2016 1PM | Ricardo | 2.15 | 12/1/2016 10PM | Ricardo
3.3 | Feedback on TestPerson Class | 12/3/2016 1PM | Kevin | 3.2 | 12/2/2016 11AM | Kevin
3.4 | Implementation of ContactList Class | 12/2/2016 1PM | Kris | 2.15 | 12/1/2016 10PM | Kris
3.5 | Feedback on ContactList Class | 12/3/2016 1PM | Ricardo | 3.4 | 12/2/2016 11AM | Ricardo
3.6 | First draft of Use Case 1 implementation to team | 12/5/2016 1PM | Ricardo | 2.15 | 12/5/2016 1PM | Ricardo
3.7 | Feedback and bug reports on draft of Use Case 1 implementation to author | 12/6/2016 1PM | Kris | 3.6 | 12/5/2016 10PM | Kris
3.8 | Second draft of Use Case 1 implementation to Elaine | 12/7/2016 1PM | Kevin | 3.7 | 12/7/2016 9:30AM | Kevin
3.9 | Feedback on Use Case 1 code from Elaine | 12/8/2016 1PM | Elaine | 3.8 | 12/7/2016 2:30PM | Elaine
Jobs required for Task 4
4.0 | First draft of Use Case 2 implementation to team | 12/11/2016 1PM | Kris | 3.9 | 12/8/2016 10PM | Kris
4.1 | First draft of Use Case 3 implementation to team | 12/11/2016 1PM | Ricardo | 3.9 | 12/9/2016 11AM | Ricardo
4.2 | First draft of Use Cases 4,5 implementation to team | 12/11/2016 1PM | Kevin | 3.9 | 12/9/2016 10PM | Kevin
4.3 | Feedback on Use Case 2 implementation to author | 12/12/2016 1PM | Ricardo | 4.0 | 12/10/2016 11AM | Ricardo
4.4 | Feedback on Use Case 3 implementation to author | 12/12/2016 1PM | Kevin | 4.1 | 12/10/2016 11AM | Kevin
4.5 | Feedback on Use Case 4,5 implementation to author | 12/12/2016 1PM | Kris | 4.2 | 12/10/2016 11AM | Kris
4.6 | First draft of GUI | 12/12/2016 11PM | Kevin | 4.3, 4.4, 4.5 | 12/11/2016 1PM | Kevin
4.7 | Final code for Use Case 2 implementation to team | 12/13/2016 1PM | Kevin | 4.3 | 12/12/2016 1PM | Kevin
4.8 | Final code for Use Case 3 implementation to team | 12/13/2016 1PM | Kris | 4.4 | 12/12/2016 9AM | Kris
4.9 | Final code for Use Cases 4,5 implementation to team | 12/13/2016 1PM | Ricardo | 4.5 | 12/12/2016 9AM | Ricardo
4.10 | Final draft of GUI | 12/13/2016 1PM | Ricardo | 4.7, 4.8, 4.9 | 12/13/2016 11PM | Ricardo
4.11 | Integration testing complete and source code submitted to Elaine | 12/14/2016 1PM | Kevin | 4.7, 4.8, 4.9, 4.10 | 12/14/2016 9AM | Kevin
4.12 | All other documents updated and submitted to Elaine | 12/14/2016 1PM | Kevin | 4.9 | 12/14/2016 9AM | Kevin
Before you submit this schedule as part of your Task 1 deliverable, fill in names, dates and times for all jobs in ALL Tasks.
The only columns to be left blank for now is the "Date and Time Completed" and "Person Completing" for Tasks 2, 3, and 4.
When you give feedback on a deliverable, you must give at least two suggestions for improvement. If you cannot show
at least two suggestions for improvement that you gave the author of a deliverable, you will not get credit for that Task.